## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | 2026-02-05 | Legacy VXML architecture documentation missing key API constraints | Sprint 1 | Analysis Team | Documentation | Updated requirements doc with ACS compatibility gaps | 2026-07-02 | Closed | Verified successfully
2 | 2026-02-12 | Incorrect mapping of existing IVR routing logic in analysis draft | Sprint 1 | Analysis Team | Functional | Corrected routing tree documentation for AI handover | 2026-02-14 | Closed | Ready for Sprint 2
3 | 2026-02-20 | Middleware API failing to connect with BAP Service | Sprint 2 | Backend Team | Integration | Fixed authentication token generation in connector | 2026-02-22 | Closed | Connection established
4 | 2026-02-26 | High latency during real-time data handling between VXML and ACS | Sprint 2 | Backend Team | Performance | Implemented payload caching and optimized JSON parsing | 2026-02-28 | Closed | Latency under 200ms
5 | 2026-03-06 | Natural language dialogue flow not triggering legacy IVR fallback | Sprint 3 | AI Team | Logic | Mapped conversational intent nodes to VXML fallback routes | 2026-03-08 | Closed | Verified via testing
6 | 2026-03-12 | Voice input module cutting off user speech prematurely | Sprint 3 | AI Team | UI/UX | Adjusted silence detection timeout in conversational interface | 2026-03-14 | Closed | Voice input stabilized
7 | 2026-03-18 | Performance degradation during full-cycle load testing | Sprint 4 | Testing Team | Performance | Scaled integration layer instances to handle concurrent calls | 2026-03-21 | Closed | Passed load test
8 | 2026-03-24 | AI flow accuracy dropping in noisy environments | Sprint 4 | AI Team | Algorithmic | Fine-tuned acoustic model thresholds for production | 2026-03-26 | Closed | Accuracy improved to 96%
9 | 2026-03-28 | Post-deployment monitoring logs not syncing real-time | Sprint 4 | Backend Team | Integration | Reconfigured log streaming endpoint in production server | 2026-03-29 | Closed | Real-time monitoring active
10 | 2026-03-31 | Minor UI alignment issue in the admin dashboard reporting | Wrap-up | Frontend Team | UI | Fixed CSS layout for final project handover | 2026-04-01 | Closed | Final verification done